## Network Diagram
NOTATION
|  | Slack |  |  | ES: Early start |  | LS: Late Start |  | Time : No. of Days | [7 empty] | CRITICAL PATH IS DEPICTED IN THICK BOLD ARROWS
ES | ID | EF |  |  | EF: Early Finish |  | LF: Late Finish |  | ID: Activity ID number
Activity Name | [16 empty] | CRITICAL PATH (in terms of ID): 1235678
LS | Time | LF
0
[9 empty] | 20 | 3 | 39
Design
[5 empty] | 0 |  |  | 0 | 20 | 19 | 39 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | 0 | 1 | 4 | 4 | 2 | 20 |  |  |  | 39 | 5 | 83 | 83 | 6 | 92 | 92 | 7 | 95 | 95 | 8 | 105
|  |  | Permission |  |  | Planning | [5 empty] | Website Development |  |  | Testing |  |  | Deployment & Payment |  |  | Training
|  |  | 0 | 4 | 4 | 4 | 16 | 20 |  |  | 4 | 39 | 44 | 83 | 83 | 9 | 92 | 92 | 3 | 95 | 95 | 10 | 105
[9 empty] | 20 | 4 | 35
Purchase
[9 empty] | 24 | 15 | 39

## Detailed Network Diagram
NOTATION
|  | Slack |  | CRITICAL PATH IS DEPICTED IN THICK BOLD ARROWS
ES | ID | EF
Activity Name
LS | Time | LF
[34 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[32 empty] | 20 | 3.1 | 23 | 23 | 3.2 | 35 | 35 | 3.3 | 36 | 36 | 3.4 | 38 | 38 | 3.5 | 39
[32 empty] | Plan graphic design concept |  |  | Draft version of graphic design |  |  | Review graphic design |  |  | Final version of graphic design |  |  | Approve graphic design
[7 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 20 | 3 | 23 | 23 | 12 | 35 | 35 | 1 | 36 | 36 | 2 | 38 | 38 | 1 | 39 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | 0 | 1.1 | 1 | 1 | 1.2 | 2 | 2 | 1.3 | 3 | 3 | 1.4 | 4 | 4 | 2.1 | 5 | 4 | 2.2 | 9 | 9 | 2.3 | 12 | 12 | 2.5 | 14 | 14 | 2.6 | 20 | [15 empty] | 39 | 5.1 | 44 | 44 | 5.2.1 | 46 | 46 | 5.2.2 | 52 | 52 | 5.2.3 | 58 | 58 | 5.2.4 | 64
|  |  | START |  | Create Project Charter |  |  | Held kick-off meeting |  |  | Present project charter |  |  | Sign project charter |  |  | Schedule team plan meet |  |  | Document the requirements |  |  | Prepare Project Schedule |  |  | Determine project cost |  |  | Fund collection | [17 empty] | Create code design document |  |  | Add department info |  |  | Add profiles to website |  |  | Add courses, mails, library |  |  | Add learning resources |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 2 |  |  | 0 |  |  | 0 |  |  | 0
[5 empty] | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 3 | 3 | 1 | 4 | 4 | 1 | 5 | 4 | 4 | 9 | 9 | 3 | 12 | 12 | 2 | 14 | 14 | 6 | 20 | [15 empty] | 39 | 5 | 44 | 44 | 2 | 46 | 46 | 6 | 52 | 52 | 6 | 58 | 58 | 6 | 64 | 64 | 5.3 | 70 | 70 | 5.4 | 83 | 83 | 6.1 | 85 | 85 | 6.2 | 87 | 87 | 6.3 | 88 | 88 | 6.4 | 89 | 89 | 6.5 | 90 | 90 | 7.1 | 91 | 91 | 7.2 | 92 | 92 | 7.3 | 93 | 93 | 8.1 | 95 | 95 | 8.2 | 98 | 98 | 8.3 | 100 | 102 | 8.4 | 103 | 103 | 8.5 | 104 | 104 | 8.6 | 105
[34 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 4 | [18 empty] | Setup the server |  |  | Implement database |  |  | Test functionality |  |  | Perform security test |  |  | Perform speed test |  |  | Test responsiveness |  |  | Report test results |  |  | Integrate website |  |  | Prepare documentation |  |  | Payment |  |  | Prepare training reports |  |  | Conduct training sessions |  |  | Create lessons learned |  |  | Upload training materials |  |  | Store backup files |  |  | Close meeting
[32 empty] | 20 | 4.1 | 25 | 20 | 4.1 | 25 | 20 | 4.1 | 25 | 20 | 4.1 | 25 | [18 empty] | 64 | 6 | 70 | 70 | 13 | 83 | 83 | 2 | 85 | 85 | 2 | 87 | 87 | 1 | 88 | 88 | 1 | 89 | 89 | 1 | 90 | 90 | 1 | 91 | 91 | 1 | 92 | 92 | 1 | 93 | 93 | 2 | 95 | 95 | 3 | 98 | 98 | 2 | 102 | 102 | 1 | 103 | 103 | 1 | 104 | 104 | 1 | 105
[32 empty] | Purchase Website domain |  |  | Purchase Website hosting |  |  | Purchase local server |  |  | Purchase networking eqiupment
[32 empty] | 20 | 5 | 25 | 20 | 5 | 25 | 20 | 5 | 25 | 20 | 5 | 25